## Sumary
Developer | Hours
Ruben | 2
Clifton | 184.3
Total: | 186.3
Project: | 300
113.7
Progress: | 13253%
Tasks: | 459 | 20 | 459

## Task List
| Task | Estimate | Ruben | Clifton | Sub Tasks | Progress | Sub Task Tab
1 | Admin |  | 0 | 1.25 | 4 | 50% | Sub Task-Admin
2 | Main Application Design and Framework |  | 1 | 6 | 2 | 75% | Sub Task-Main Project Design
3 | Main DB |  | 0 | 3.5 | 3 | 96.67% | Sub Task-Main Database
4 | Clients |  | 0 | 26 | 14 | 100% | Sub Task-Client
5 | Client Types |  | 0 | 4 | 5 | 100% | Sub Task-Client Type
6 | Products |  | 0 | 6 | 8 | 100% | Sub Task-Products
7 | Subscription |  | 0 | 4 | 9 | 100% | Sub Task-Subsciption
8 | Financials |  | 0 | 9 | 3 | 90% | Sub Task-Financials
9 | Debit Orders - Not Linked To Anything |  | 0 | 0.75 | 4 | 45% | Sub Task-Debit Order
10 | Queries (Support Tickets) |  | 0 | 12 | 6 | 73.33% | Sub Task-Queries
11 | Telesales |  | 0 | 10 | 6 | 56.67% | Sub Task TeleSales
12 | SMS - Not linked to anything |  | 0 | 31.5 | 6 | 100% | Sub Task-SMS
13 | Security |  | 0 | 6 | 7 | 100% | Sub Task-Security
14 | Reports |  | 0 | 0 | 1 | 0% | Sub Task-Template
15 | Shipping |  | 0 | 0 | 3 | 0% | Sub Task-Shipping
16 | Obligations |  | 0 | 0 | 1 | 0% | Sub Task-Template
17 | System |  | 0 | 0 | 1 | 0% | Sub Task-Template
18 | Account Administration |  | 0 | 2 | 1 | 100% | Sub Task-Template
19 | Agile changes / fixes |  | 0 | 52.3 | 41 | 92.68% | Agile
20 | Implementation And Integration |  | 0 | 10 | 4 | 100% | Sub Implementation Integration
184.3
|  | Claims |  |  | Ruben | Clifton |  | Rate
|  | Cycle | Hours
|  | 1 | 1 | 74 | 330 | 24420 |  | 330
|  | 2 | 0 | 110.3 | 0 | 36399 |  | 330
330
330
330
330
330
330
330
330

## Sub Task-Shipping
No | Description | Ruben | Clifton | Progress | Info
1 | Table design | 0 | 0 | 0%
2 | Form design | 0 | 0 | 0%
3 | Link currier postal code and extra cost | 0 | 0 | 0%

## Sub Task TeleSales
No | Description | Ruben | Clifton | Progress | Info
1 | Functional design |  | 0.5 | 50%
2 | Database Design |  | 0.5 | 50%
3 | Create data access models and tables |  | 0.5 | 100%
4 | Create client form display and sales history |  | 3 | 20%
5 | Create order form |  | 4 | 20%
6 | Order Status Lookup - Populate, Create Edit Delete - add to menu items |  | 1.5 | 100%

## Sub Implementation Integration
No | Description | Ruben | Clifton | Progress | Info
1 | Roll out new version 18/09/2015 | 0 | 2 | 100%
2 | Data merge on new version 18/09/2015 | 0 | 4 | 100%
3 | Data merge and new version 26/10/2015 | 0 | 2 | 100%
4 | Data merge and new version 02/11/2015 | 0 | 2 | 100%

## Agile
No | Description | Ruben | Clifton | Progress | Info
1 | Update Logo | 0 | 0.75 | 100%
2 | Display big logo at login | 0 | 0.5 | 100%
3 | Fix client capture to flow like application form | 0 | 4 | 100% | Title | x
[5 empty] | Home Language | x
[5 empty] | Ethnic Group | x
[5 empty] | Surname | x
[5 empty] | Initials | x
[5 empty] | Employer | x
[5 empty] | Full Names | x
[5 empty] | Monthly Income | x
[5 empty] | Nick Name | x
[5 empty] | Date of Birth | dd/mm/yyyy
[5 empty] | Occupation | x
[5 empty] | ID Number | x
[5 empty] | SA Resident | x
Delivery Address
Postal Address
4 | Birthdate no time | 0 | 4 | 100%
5 | Change Titel to Title (Database, models views and controllers) | 0 | 1.25 | 100%
6 | Change Product price to dependent on product and Client type | 0 | 5 | 100%
Clients;
7 | Add Active to client and remove delete function | 0 | 1 | 100%
8 | Birthdate calendar start date at 1940 | 0 | 0.5 | 100%
9 | Language not saving or not loading correctly | 0 | 1 | 100%
10 | Update client if the ID already exists | 0 | 3.5 | 100%
11 | Detail section Language not displaying correctly | 0 | 0.25 | 100%
12 | Display Active subscriptions and banking detail on client detail screen | 0 | 3 | 100%
13 | Add Client subscriptions and banking detail to user rights | 0 | 0.25 | 100%
14 | Add Client distributor | 0 | 0.25 | 100%
Subscription Products;
15 | Add valid from date on price | 0 | 1 | 100%
16 | Subscription product active must be used when displaying subscription | 0 | 3 | 100%
17 | Refresh on page prevent duplicate product selection | 0 | 0.25 | 100%
18 | Op klient 10002, wanneer ek na ‘Go to Banking” gaan, gee hy nog steeds die error screen. Ek het nie ‘n probleem met enige van die ander nie. Ek kan dus nie die bank besonderhede update nie. | 0 | 1 | 100%
19 | Dan moet ons ook die adresse lyne 5 lyne maak (saam met poskode). 4 is net te min vir langer adresse. | 0 | 0.3 | 100%
20 | “Create New” op die kliente lys werk nie. Gee error. | 0 | 0.3 | 100%
21 | Op die “Client List” moet ons ook die status van beide die klient en die debietorder moet kan sien. | 0 | 0.5 | 100%
22 | Ek neem aan die ‘Supplier Code” bo aan die ”Capture” en “Client Edit” screens is die “Reseller Code”. Kan nerens sien waar ek die benaming kan verander nie. Ons moet net dink hoe benader ons in stelsel as ‘n Reseller verder aan ‘n “Distributor” gekoppel is. Vir bespreking. | 0 | 0.3 | 100%
23 | Wanneer jy uit die client list na “Details” click, is al die velde wat in die capture vorm is nie in die lys nie. (Het in vorige emails geopper) Jy kan byvoorbeeld slegs die epos adres in die “banking screen” edit. Die details lys behoort ook die klient nommer te gee. | 0 | 0.5 | 100%
24 | Wanneer ek klient 1006 se poskode edit en save, kry ek die volgende error. Error. An error occurred while processing your request. | 0 | 1 | 100%
25 | In die ‘Client Details” screen wys die adresse as “Addressid” vir beide. Die benamings moet wees “Postal Address” en Delivery Address” | 0 | 0.3 | 100%
26 | Dink ook bo aan die “client details” skerm moet die “Client Status” ook wys. | 0 | 0.3 | 100%
27 | Ek is ingelog in “Admin”. Wanneer ek uit die “User” menu die “Capture Application” click, gee hy weer die error. “Error. An error occurred while processing your request.” | 0 | 0.3 | 100%
28 | Wanneer jy die subscription produk kies en “Active” maak, behoort die banking details ook “Active” te wees. Indien nie, behoort ‘n boodskap op skerm dit te wys. Of die stelsel moet default na die banking skerm as jy subskripsie produk aktief maak, en vice versa. Dink dalk boodskap is beter. | 0 | 1.5 | 100%
29 | Fix access right issue | 0 | 0.5 | 100%
30 | Investigate speed issue | 0 | 4 | 100%
31 | Client Subscription Edit | 0 | 1 | 100%
32 | Dynamic user menu | 0 | 8 | 100%
33 | Sort user menus | 0 | 1 | 100%
34 | Put Client type on menu | 0 | 0.25 | 100%
35 | Search on Client Type under Client | 0 | 0.25 | 100%
36 | SMS T -> Province | 0 | 0.25 | 100%
37 | SMS Char Count | 0 | 1 | 100%
38 | Add another address line | 0 | 0.25 | 100%
39 | Add Business name and registration number | 0 | 0 | 0%
40 | finClientAccounts crash | 0 | 0 | 0%
41 | Add warning if id number exists | 0 | 0 | 0%

## Sub Task-Queries
No | Description | Ruben | Clifton | Progress
1 | Design tale | 0 | 0.25 | 90%
2 | Create data object | 0 | 0.25 | 90%
3 | Templates | 0 | 4 | 0%
4 | Capture | 0 | 1 | 100%
5 | Manage | 0 | 4 | 80%
6 | User Search | 0 | 2.5 | 80%

## Sub Task-SMS
No | Description | Ruben | Clifton | Progress
1 | Design tale | 0 | 0.25 | 90%
2 | Create data object | 0 | 0.25 | 90%
3 | Templates | 0 | 7 | 90%
4 | SMS Management | 0 | 17 | 90%
5 | Free Text SMS | 0 | 3 | 100%
6 | SMS from Client view | 0 | 4 | 100%

## Sub Task-Subsciption
No | Description | Ruben | Clifton | Progress
1 | Table design | 0 | 0.5 | 90%
2 | Data access models | 0 | 0.5 | 90%
3 | Display models | 0 | 0.5 | 50%
4 | List view | 0 | 0.25 | 50%
5 | Single view | 0 | 0.25 | 50%
6 | Edit view | 0 | 0.25 | 50%
7 | Assosiated Lookups and links | 0 | 1.5 | 100%
8 | Unit Test | 0 | 0.25 | 100%
9 | Change quantity on Client subscription | 0 | 0 | 0%

## Sub Task-Admin
No | Description | Ruben | Clifton | Progress
1 | Create Git repository, set up source tree - Clifton PC |  | 0.25 | 100%
2 | Create project admin sheet |  | 1 | 100%
3 | Set up Git account - Ruben |  |  | 0%
4 | Set up Source tree - Ruben PC |  |  | 0%

## Sub Task-Main Project Design
No | Description | Ruben | Clifton | Progress
1 | Base object Identification | 1 | 0 | 100%
2 | Overall design |  | 6 | 50%

## Sub Task-Main Database
No | Description | Ruben | Clifton | Progress
1 | Create database | 0 | 0.25 | 100%
2 | Set up application security tables | 0 | 0.25 | 100%
3 | Create Lookups according to application form | 0 | 3 | 90%

## Sub Task-Template
No | Description | Ruben | Clifton | Progress
1 | Task Description | 0 | 0 | 0%

## Sub Task-Debit Order
No | Description | Ruben | Clifton | Progress
1 | Table design | 0 | 0.5 | 90%
2 | Admin functions | 0 | 0.25 | 90%
3 | Create debit order for client Stored procedure | 0 | 0 | 0%
4 | Create debit order for client view | 0 | 0 | 0%

## Sub Task-Financials
No | Description | Ruben | Clifton | Progress
1 | Table design | 0 | 1 | 90%
2 | Create journal stored procedure | 0 | 6 | 90%
3 | Create Data models | 0 | 2 | 90%

## Sub Task-Products
No | Description | Ruben | Clifton | Progress
1 | Table design | 0 | 0.5 | 90%
2 | Data access models | 0 | 0.75 | 90%
3 | Display models | 0 | 1 | 50%
4 | List view | 0 | 0.25 | 50%
5 | Single view | 0 | 0.25 | 50%
6 | Edit view | 0 | 0.25 | 50%
7 | Assosiated Lookups and links | 0 | 1 | 100%
8 | Unit Test | 0 | 2 | 100%

## Sub Task-Client
No | Description | Ruben | Clifton | Progress
1 | Client Table design | 0 | 2.5 | 90%
2 | Cliend data access models | 0 | 2.5 | 90%
3 | Client display models | 0 | 0.25 | 50%
4 | Client list view | 0 | 0.25 | 50%
5 | Client single view | 0 | 0.25 | 50%
6 | Client edit view | 0 | 2 | 50%
7 | Client Client type link | 0 | 0.25 | 100%
8 | Unit Test | 0 | 3 | 100%
9 | Create client search partial view | 0 | 3 | 0%
10 | User function - Capture application form | 0 | 2 | 80%
11 | Create address management partial view | 0 | 3 | 15%
12 | Create contact management partial view | 0 | 0 | 0%
13 | Date Picker view | 0 | 3 | 20%
14 | Client Datacapture form |  | 4 | 80%

## Sub Task-Client Type
No | Description | Ruben | Clifton | Progress
1 | Client Type table design | 0 | 0.5 | 100%
2 | Clien Type data access models | 0 | 1.5 | 100%
3 | Client Type display models | 0 | 0.5 | 50%
4 | Client Type list view and edit | 0 | 0.5 | 50%
5 | Unit Test | 0 | 1 | 100%

## Sub Task-Security
No | Description | Ruben | Clifton | Progress
1 | Security Table design | 0 | 0 | 100%
2 | Security data access models | 0 | 0.5 | 100%
3 | Security display models | 0 | 0.5 | 50%
4 | Link user roles | 0 | 1 | 100%
5 | Update Git | 0 | 0 | 0%
6 | Unit Test | 0 | 2 | 100%
7 | User Management | 0 | 2 | 100%