## Sumary
Developer | Hours
Ruben | 2
Clifton | 88
Total: | 90
Project: | 300
210
Progress: | 7017%
Tasks: | 414 | 19 | 414

## Task List
| Task | Estimate | Ruben | Clifton | Sub Tasks | Progress | Sub Task Tab
1 | Admin |  | 0 | 1.25 | 4 | 50% | Sub Task-Admin
2 | Main Application Design and Framework |  | 1 | 6 | 2 | 75% | Sub Task-Main Project Design
3 | Main DB |  | 0 | 3.5 | 3 | 96.67% | Sub Task-Main Database
4 | Clients |  | 0 | 26 | 14 | 55.36% | Sub Task-Client
5 | Client Types |  | 0 | 4 | 5 | 80% | Sub Task-Client Type
6 | Products |  | 0 | 6 | 8 | 72.5% | Sub Task-Products
7 | Subscription |  | 0 | 4 | 8 | 72.5% | Sub Task-Subsciption
8 | Financials |  | 0 | 5 | 3 | 90% | Sub Task-Financials
9 | Debit Orders - Not Linked To Anything |  | 0 | 0.75 | 4 | 45% | Sub Task-Debit Order
10 | Queries (Support Tickets) |  | 0 | 0.5 | 2 | 90% | Sub Task-Queries
11 | Telesales |  | 0 | 0 | 1 | 0% | Sub Task-Template
12 | SMS - Not linked to anything |  | 0 | 0.5 | 2 | 90% | Sub Task-SMS
13 | Security |  | 0 | 1 | 6 | 50% | Sub Task-Security
14 | Reports |  | 0 | 0 | 1 | 0% | Sub Task-Template
15 | Business Processes |  | 0 | 0 | 1 | 0% | Sub Task-Template
16 | Obligations |  | 0 | 0 | 1 | 0% | Sub Task-Template
17 | System |  | 0 | 0 | 1 | 0% | Sub Task-Template
18 | Account Administration |  | 0 | 0 | 1 | 0% | Sub Task-Template
19 | Agile changes / fixes |  | 0 | 29.5 | 17 | 100% | Agile
88
|  | Claims |  |  | Ruben | Clifton |  | Rate
|  | Cycle | Hours
|  | 1 | 1 | 74 | 330 | 24420 |  | 330
|  | 2 | 0 | 14 | 0 | 4620 |  | 330
330
330
330
330
330
330
330
330

## Agile
No | Description | Ruben | Clifton | Progress | Info
1 | Update Logo | 0 | 0.75 | 100%
2 | Display big logo at login | 0 | 0.5 | 100%
3 | Fix client capture to flow like application form | 0 | 4 | 100% | Title | x
[5 empty] | Home Language | x
[5 empty] | Ethnic Group | x
[5 empty] | Surname | x
[5 empty] | Initials | x
[5 empty] | Employer | x
[5 empty] | Full Names | x
[5 empty] | Monthly Income | x
[5 empty] | Nick Name | x
[5 empty] | Date of Birth | dd/mm/yyyy
[5 empty] | Occupation | x
[5 empty] | ID Number | x
[5 empty] | SA Resident | x
Delivery Address
Postal Address
4 | Birthdate no time | 0 | 4 | 100%
5 | Change Titel to Title (Database, models views and controllers) | 0 | 1.25 | 100%
6 | Change Product price to dependent on product and Client type | 0 | 5 | 100%
Clients;
7 | Add Active to client and remove delete function | 0 | 1 | 100%
8 | Birthdate calendar start date at 1940 | 0 | 0.5 | 100%
9 | Language not saving or not loading correctly | 0 | 1 | 100%
10 | Update client if the ID already exists | 0 | 3.5 | 100%
11 | Detail section Language not displaying correctly | 0 | 0.25 | 100%
12 | Display Active subscriptions and banking detail on client detail screen | 0 | 3 | 100%
13 | Add Client subscriptions and banking detail to user rights | 0 | 0.25 | 100%
14 | Add Client distributor | 0 | 0.25 | 100%
Subscription Products;
15 | Add valid from date on price | 0 | 1 | 100%
16 | Subscription product active must be used when displaying subscription | 0 | 3 | 100%
17 | Refresh on page prevent duplicate product selection | 0 | 0.25 | 100%

## Sub Task-Queries
No | Description | Ruben | Clifton | Progress
1 | Design tale | 0 | 0.25 | 90%
2 | Create data object | 0 | 0.25 | 90%

## Sub Task-SMS
No | Description | Ruben | Clifton | Progress
1 | Design tale | 0 | 0.25 | 90%
2 | Create data object | 0 | 0.25 | 90%

## Sub Task-Subsciption
No | Description | Ruben | Clifton | Progress
1 | Table design | 0 | 0.5 | 90%
2 | Data access models | 0 | 0.5 | 90%
3 | Display models | 0 | 0.5 | 50%
4 | List view | 0 | 0.25 | 50%
5 | Single view | 0 | 0.25 | 50%
6 | Edit view | 0 | 0.25 | 50%
7 | Assosiated Lookups and links | 0 | 1.5 | 100%
8 | Unit Test | 0 | 0.25 | 100%

## Sub Task-Admin
No | Description | Ruben | Clifton | Progress
1 | Create Git repository, set up source tree - Clifton PC |  | 0.25 | 100%
2 | Create project admin sheet |  | 1 | 100%
3 | Set up Git account - Ruben |  |  | 0%
4 | Set up Source tree - Ruben PC |  |  | 0%

## Sub Task-Main Project Design
No | Description | Ruben | Clifton | Progress
1 | Base object Identification | 1 | 0 | 100%
2 | Overall design |  | 6 | 50%

## Sub Task-Main Database
No | Description | Ruben | Clifton | Progress
1 | Create database | 0 | 0.25 | 100%
2 | Set up application security tables | 0 | 0.25 | 100%
3 | Create Lookups according to application form | 0 | 3 | 90%

## Sub Task-Template
No | Description | Ruben | Clifton | Progress
1 | Task Description | 0 | 0 | 0%

## Sub Task-Debit Order
No | Description | Ruben | Clifton | Progress
1 | Table design | 0 | 0.5 | 90%
2 | Admin functions | 0 | 0.25 | 90%
3 | Create debit order for client Stored procedure | 0 | 0 | 0%
4 | Create debit order for client view | 0 | 0 | 0%

## Sub Task-Financials
No | Description | Ruben | Clifton | Progress
1 | Table design | 0 | 1 | 90%
2 | Create journal stored procedure | 0 | 2 | 90%
3 | Create Data models | 0 | 2 | 90%

## Sub Task-Products
No | Description | Ruben | Clifton | Progress
1 | Table design | 0 | 0.5 | 90%
2 | Data access models | 0 | 0.75 | 90%
3 | Display models | 0 | 1 | 50%
4 | List view | 0 | 0.25 | 50%
5 | Single view | 0 | 0.25 | 50%
6 | Edit view | 0 | 0.25 | 50%
7 | Assosiated Lookups and links | 0 | 1 | 100%
8 | Unit Test | 0 | 2 | 100%

## Sub Task-Client
No | Description | Ruben | Clifton | Progress
1 | Client Table design | 0 | 2.5 | 90%
2 | Cliend data access models | 0 | 2.5 | 90%
3 | Client display models | 0 | 0.25 | 50%
4 | Client list view | 0 | 0.25 | 50%
5 | Client single view | 0 | 0.25 | 50%
6 | Client edit view | 0 | 2 | 50%
7 | Client Client type link | 0 | 0.25 | 100%
8 | Unit Test | 0 | 3 | 100%
9 | Create client search partial view | 0 | 3 | 0%
10 | User function - Capture application form | 0 | 2 | 80%
11 | Create address management partial view | 0 | 3 | 15%
12 | Create contact management partial view | 0 | 0 | 0%
13 | Date Picker view | 0 | 3 | 20%
14 | Client Datacapture form |  | 4 | 80%

## Sub Task-Client Type
No | Description | Ruben | Clifton | Progress
1 | Client Type table design | 0 | 0.5 | 100%
2 | Clien Type data access models | 0 | 1.5 | 100%
3 | Client Type display models | 0 | 0.5 | 50%
4 | Client Type list view and edit | 0 | 0.5 | 50%
5 | Unit Test | 0 | 1 | 100%

## Sub Task-Security
No | Description | Ruben | Clifton | Progress
1 | Security Table design | 0 | 0 | 100%
2 | Security data access models | 0 | 0 | 100%
3 | Security display models | 0 | 0 | 50%
4 | Link user roles | 0 | 0 | 0%
5 | Update Git | 0 | 0 | 0%
6 | Unit Test | 0 | 1 | 50%