## Sumary
Developer | Hours
Ruben | 1
Clifton | 9.25
Total: | 10.25
Project: | 300
289.75
Progress: | 10.56%
Tasks: | 40 | 18 | 40

## Task List
| Task | Estimate | Ruben | Clifton | Sub Tasks | Progress | Sub Task Tab
1 | Admin |  | 0 | 1.25 | 4 | 50% | Sub Task-Admin
2 | Main Appliction Design and Framework |  | 1 | 0 | 1 | 100% | Sub Task-Main Project Design
3 | Main DB |  | 0 | 0.5 | 2 | 100% | Sub Task-Main Database
4 | Clients |  | 0 | 2.5 | 9 | 55.56% | Sub Task-Client
5 | Client Types |  | 0 | 4 | 6 | 66.67% | Sub Task-Client Type
6 | Products |  | 0 | 0 | 1 | 0% | Sub Task-Template
7 | Subscription |  | 0 | 0 | 1 | 0% | Sub Task-Template
8 | Financials |  | 0 | 0 | 1 | 0% | Sub Task-Template
9 | Debit Orders - Not Linked To Anything |  | 0 | 0 | 1 | 0% | Sub Task-Template
10 | Queries |  | 0 | 0 | 1 | 0% | Sub Task-Template
11 | Telesales |  | 0 | 0 | 1 | 0% | Sub Task-Template
12 | SMS - Not linked to anything |  | 0 | 0 | 1 | 0% | Sub Task-Template
13 | Security |  | 0 | 1 | 6 | 50% | Sub Task-Security
14 | Reports |  | 0 | 0 | 1 | 0% | Sub Task-Template
15 | Business Processes |  | 0 | 0 | 1 | 0% | Sub Task-Template
16 | Obligtions |  | 0 | 0 | 1 | 0% | Sub Task-Template
17 | System |  | 0 | 0 | 1 | 0% | Sub Task-Template
18 | Account Administration |  | 0 | 0 | 1 | 0% | Sub Task-Template

## Sub Task-Admin
No | Description | Ruben | Clifton | Progress
1 | Create Git repository, set up source tree - Clifton PC |  | 0.25 | 100%
2 | Create project admin sheet |  | 1 | 100%
3 | Set up Git account - Ruben |  |  | 0%
4 | Set up Source tree - Ruben PC |  |  | 0%

## Sub Task-Main Project Design
No | Description | Ruben | Clifton | Progress
1 | Base object Identification | 1 | 0 | 100%

## Sub Task-Main Database
No | Description | Ruben | Clifton | Progress
1 | Create database | 0 | 0.25 | 100%
2 | Set up application security tables | 0 | 0.25 | 100%

## Sub Task-Template
No | Description | Ruben | Clifton | Progress
1 | Task Description | 0 | 0 | 0%

## Sub Task-Client
No | Description | Ruben | Clifton | Progress
1 | Client Table design | 0 | 0.5 | 50%
2 | Cliend data access models | 0 | 0.5 | 50%
3 | Client display models | 0 | 0.25 | 50%
4 | Client list view | 0 | 0.25 | 50%
5 | Client single view | 0 | 0.25 | 50%
6 | Client edit view | 0 | 0.25 | 50%
7 | Client Client type link | 0 | 0.25 | 100%
8 | Update Git | 0 | 0 | 0%
9 | Unit Test | 0 | 0.25 | 100%

## Sub Task-Client Type
No | Description | Ruben | Clifton | Progress
1 | Client Type table design | 0 | 0.5 | 100%
2 | Clien Type data access models | 0 | 1.5 | 100%
3 | Client Type display models | 0 | 0.5 | 50%
4 | Client Type list view and edit | 0 | 0.5 | 50%
5 | Update Git | 0 | 0 | 0%
6 | Unit Test | 0 | 1 | 100%

## Sub Task-Security
No | Description | Ruben | Clifton | Progress
1 | Security Table design | 0 | 0 | 100%
2 | Security data access models | 0 | 0 | 100%
3 | Security display models | 0 | 0 | 50%
4 | Link user roles | 0 | 0 | 0%
5 | Update Git | 0 | 0 | 0%
6 | Unit Test | 0 | 1 | 50%